## Site Diary
SITE DIARY
Project: __________ Site Engineer: __________
Date | Weather AM | Weather PM | Skilled Labour | Unskilled Labour | Work Done Today | Materials Received | Equipment on Site | Visitors / Instructions | Remarks
2026-09-28 | Sunny | Cloudy | 8 | 14 | RCC slab casting - Block A first floor; curing of columns | Cement 50 bags; 20mm aggregate 1 trip | Concrete mixer 1; vibrator 2 | Client visit - approved slab level | Slab casting completed by 4 PM
2026-09-29 | Sunny | Sunny | 9 | 15 | Brickwork - Block B ground floor walls; plaster prep | First-class bricks 3000 nos; sand 1 trip | Mixer 1; scaffolding set | Consultant - instructed to increase curing to 14 days | Curing in progress for Block A slab
2026-09-30 | Rain AM | Cloudy | 7 | 12 | Plastering - Block A ground floor; brickwork continued | Cement 30 bags | Mixer 1 | - | Rain delayed start by 1 hr
2026-10-01 | Sunny | Sunny | 10 | 16 | RCC columns - Block B ground floor; shuttering for beam B2 | 12mm rebar 1.2 MT; binding wire 10 kg | Mixer 1; vibrator 2; bar cutter | Structural engineer - checked rebar laps | Column concrete poured, 6 nos
2026-10-02 | Sunny | Sunny | 8 | 13 | Curing; formwork removal - Block A slab soffit | - | Water pump 1 | - | Cube samples taken for 7-day test
2026-10-03 | Cloudy | Rain PM | 6 | 10 | Half day - plaster touch-up; site cleanup | - | - | Weekly progress review with client | Weekly report submitted
2026-10-04 | Sunday | Holiday | - | - | Site closed - weekly holiday | - | - | - | -